## Sheet1
Risk Assessment | [5 empty] | Event | General RA | [6 empty] | 39
0-10 weighted scales - see key | [5 empty] | Date | 2012-07-11 | [6 empty] | 29
19
[5 empty] | Initial Risk | [5 empty] | Managed Risk
Item |  | Hazard and effect | Site/date | To whom | Hazard Index | Frequency Index | Risk Product | Minimise risk by | Responsible | Monitored by | Hazard Index | Frequency Index | Risk Product
1 | 1 | Mass explosion of entire holding on site leading to onsite risk | Site | Operators | 10 | 3 | 30 | Stock to remain boxed until loaded. Stock to be segregated fby competitor. | Competitor | Competitor | 10 | 1 | 10
2 | 1 | Mass explosion of entire holding in storage leading to off site fatality etc | Site | Public | 10 | 2 | 20 | Maintain safety distances to barrier for public. No access to site for public. Crew/staff ID badges. | Competitor | Security | 10 | 1 | 10
3 | 1.5 | Communication from one firing site to another | Site | Operators | 10 | 2 | 20 | Establish emergency procedures to evacuate adjacent sites. Sites to be separated by >5m | Competitor | Adjudicator | 10 | 1 | 10
4 | 1.5 | Unexpected violent event from ignition due to incorrect types | Site | Operators/Public | 10 | 2 | 20 | Good housekeeping, labelling of boxes, clear instructions and monitoring | Competitor | Competitor | 10 | 1 | 10
5 | 1.5 | Ignition through poor handling of items/containers | Site | Operator | 10 | 2 | 20 | Clear procedures from competitors and monitoring | Competitor | Competitor | 10 | 1 | 10
6 | 1.5 | Protestor attack leading to compromising safety of site | Site | Public | 10 | 2 | 20 | Adequate security | Security | Adjudicator | 10 | 1 | 10
7 | 1.5 | Accidental ignition during loading/unloading | Site | Operators | 10 | 1 | 10 | Restrict numbers of personnel and stock at any one point in time | Competitor | Competitor | 10 | 1 | 10
8 | 1.5 | Premature ignition from smoking/matches etc | Site | Operator | 10 | 2 | 20 | All sources of ignition banned from working site | Competitor | Adjudicator | 10 | 1 | 10
9 | 1.5 | Transport of fireworks from vehicle to working area | Site | Operator | 10 | 2 | 20 | Boxes to be closed. Procedures to prevent excessive quantity/unsafe transport (eg overloaded trolley) being used | Competitor | Competitor | 10 | 1 | 10
10 | 1.5 | Adding electric fuses to piped match/firework body | Site | Operator | 8 | 3 | 24 | Exposed fireworks to be kept to minimum. Igniters to be protected by sheath or similar | Competitor | Competitor | 8 | 1 | 8
11 | 1.5 | Manipulation of blackmatch fuse | Site | Operator | 8 | 2 | 16 | Exposed quanity to be kept to a minimum | Competitor | Competitor | 8 | 1 | 8
12 | 1.5 | Adding delay fuse to existing firework | Site | Operator | 8 | 2 | 16 | Exposed quanity to be kept to a minimum | Competitor | Competitor | 8 | 1 | 8
13 | 1.5 | Packing of fireworks for transport | Site | Operator | 8 | 2 | 16 | Exposed quanity to be kept to a minimum. Approved packaging and methods | Competitor | Competitor | 8 | 1 | 8
14 | 1.5 | Loading vehicle | Vehicle | Operator | 8 | 2 | 16 | Good manual handling, monitoring etc | Competitor | Competitor | 8 | 1 | 8
15 | 1.5 | Collapse of stack of fireworks in vehicle leading to ignition | Vehicle | Operator | 8 | 2 | 16 | Good manual handling, monitoring etc | Competitor | Competitor | 8 | 1 | 8
16 | 1.5 | Premature ignition of fireworks while loading vehicle due to poor handling | Vehicle | Operator | 8 | 2 | 16 | Good manual handling, monitoring etc | Competitor | Competitor | 8 | 1 | 8
17 | 1.5 | Premature ignition of igniter whilst in vehicle | Vehicle | Operator | 10 | 2 | 20 | All wires "shunted". Transmission equipment prohibited from loading area | Competitor | Competitor | 10 | 1 | 10
18 | 1.5 | Transport of fireworks | Vehicle | Operator/Public | 10 | 3 | 30 | Training of drivers, road awareness etc | Competitor | Competitor | 10 | 2 | 20
19 | 1.5 | TESA Determination of firework types | Prior to Display | Public | 10 | 3 | 30 | Maximum calibres determined to minimise fall-out (see fallout table) | Competitor | Adjudicator | 10 | 1 | 10
20 | 2 | Adverse fallout predicted prior to display | Display | Public | 10 | 3 | 30 | Display curtailed to minimise fall-out (see fallout table) | Competitor | Adjudicator | 6 | 1 | 6
21 | 2 | Wind change in speed/direction during setup | Prior to Display | Public | 10 | 3 | 30 | Display curtailed to minimise fall-out (see fallout table) | Competitor | Adjudicator | 6 | 1 | 6
22 | 2 | Wind change in speed/direction during display | Display | Public | 10 | 3 | 30 | Display curtailed to minimise fall-out (see fallout table) | Competitor | Adjudicator | 6 | 1 | 6
23 | 2 | Fallout during display as advised by marshalls etc | Display | Public | 10 | 3 | 30 | Displays stopped by radio | Competitor | Adjudicator | 6 | 1 | 6
24 | 2 | Accident on site during display | Display | Operator | 10 | 3 | 30 | First Aid available - communication to emergency services via event organisers | Competitor | Adjudicator | 10 | 1 | 10
25 | 2 | Premature ignition of fireworks from misfire | Display | Operator | 10 | 3 | 30 | Material setup/protected to minimise misfires | Competitor | Competitor | 10 | 2 | 20
26 | 2 | Unauthorised personnel entering site during firing | Display | Public | 10 | 3 | 30 | Adequate security on access points by land. Exclusion zone maintained. In case security breah display stopped by adjudicator | Security | Adjudicator | 10 | 2 | 20
27 | 2 | Premature ignition from other company's fall-out | Display | Operator | 10 | 3 | 30 | Crews not permitted in firing areas. Fireworks protected | Competitor | Competitor | 10 | 2 | 20
28 | 2 | Accident during clearing up | After Display | Operator | 10 | 3 | 30 | No clear up on individual sites until 20minutes after display end | Competitor | Competitor | 10 | 1 | 10
29 | 2 | Unauthorised access during clear up | After Display | Operator | 10 | 3 | 30 | Marshalls to remain on site until site completely clear | Security | Security | 10 | 1 | 10
30 | 2 | [5 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0